## Sheet1
Tasks | 2022-09-22 | 2022-10-22 | 2022-11-22 | 2022-12-22 | 2022-01-22 | 2022-02-22 | 2022-03-22 | 2022-04-22 | 2022-05-22
Gather and process data inputs
Initiate GitHub repository
Indicator search
Indicator selection
Write code to retrieve and process all datasets | [5 empty] | Milestone
Calculate environmental vulnerability index
Raster data: calculate average within prison polygon boundaries
Vector data: calculate proximity from prison boundaries
Convert all raw values to percentiles
Calculate environmental vulnerability index for each prison | [6 empty] | Milestone
Data sharing
Prepare and publish code and detailed documentation | [8 empty] | Milestone
Process and publish final dataset to open-source platforms | [8 empty] | Milestone
Manuscript preparation and submit for publication | [8 empty] | Milestone